|  | ISO/IEC JTC1/SC 35 – User Interfaces SC 35N0334/Rev. |
| --- | --- |

ISO

ORGANISATION INTERNATIONALE DE NORMALISATION

INTERNATIONAL ORGANIZATION FOR STANDARDIZATION



CEI (IEC)

COMMISSION ÉLECTROTECHNIQUE INTERNATIONALE

INTERNATIONAL ELECTROTECHNICAL COMMISSION



Title	Revised Business plan for JTC 1/SC 35 – User interfaces to JTC 1 Plenary

Status	This document is in response to Resolution 8, “Request to SC 35”,

adopted at the Sixteenth Meeting of ISO/IEC JTC 1, 29th October -

2nd November 2001, Kohala Coast, Island of Hawai

Source 	SC 35 Secretariat

Action identifier	For information

Date assigned	2001-11-23

Number of pages	7

# BUSINESS PLAN FOR JTC 1/SC 35 - User Interfaces

Period covered: October  2000 - September 2001

Submitted by:  ISO/IEC JTC 1/SC 35 – User Interfaces

1. MANAGEMENT SUMMARY:

1a REMARKS

SC 35 held two Plenary meetings respectively in Québec, France (22th - 26th November 2000), and Stockholm, Sweden (5th - 6th July 2001).

1.1 JTC 1/SC 35 STATEMENT OF SCOPE

- The current approved scope for ISO/IEC JTC 1/SC 35 is:

“Standardization in the field of User-system interfaces between users (including people with special needs) and systems encompassing input and output devices in information technology environments, with a priority of meeting the JTC 1 requirements for cultural and linguistic adaptability”.

Included are the following related areas:

- Interfaces between users and devices such as keyboard, mice, pointers, pens; visual displays, and forms of audio and tactile input/output, with the emphasis on functionality

- Rules for system control by voice, vision, movement, gestures, etc.

- Presentation techniques, icons, graphical symbols, etc.

- Dialogue control and navigation in interactions between humans and systems assistance and tutoring

- 1.2 PROJECT REPORT

- The table below gives an overview of current standardization projects included in the JTC 1/SC 35 Program of Work with specification of the related responsible Working Group:

- WG 1	Keyboard and input interfaces

- WG 2	User interface interaction

- WG 3	Graphical symbols

- WG 4	User interfaces for mobile devices

- WG 5	Cultural, Linguistic and User Requirements

- WG 6	User interfaces for disabled and elderly people

| - Project - Number: | - Title | - Ref. | - W G | ## NP | - WD | - CD/ ### FCD | ### FDIS | ## IS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - JTC 1 - 18.21.02.04 | - ISO/IEC 11581-4 - Icon symbols & functions - Part 4: Control icons | - N0125 | - WG 2 - WG 2 |  | - 95/07 | - 2nd CD - 01/11 | - 02/05 | - 02/11 |
| - JTC 1 - 18.21.02.05 | - ISO/IEC 11581-5 - Icon symbols & functions - Part 5: Tool icons | - N0166 - (N0309 - FDIS) | - WG 2 |  | - 95/07 | - FCD - 00/12 | - 01/11 | - 02/03 |
| - JTC 1 - 18.52 | - ISO/IEC 13251 - Collective standard - Gra- - phical symbols for office - equipment | - N0225 - (N0321 - FCD) | - WG 3 |  | - 1995 | - FCD - 01/06 | - 01/11 | - 02/03 |
| - JTC 1 - 18.09.02 | - ISO/IEC 9995-2 - 1994 - Information technology - - Keyboard layouts for text - and office systems - Part 2 : - Alphanumeric section - REVISION | - IS 1994 - N0191 - (N0302 - FCD) | - WG 1 | - Revision | - 00/11 | - FCD - 01/11 | - 02/06 | - 02/12 |
| - JTC1 - 18.09.03 | - ISO/IEC 9995-3: 1994 - Information technology - - Keyboard layouts for text - and office systems - Part 3 : - Complementary layouts - of the alphanumeric zone - of the alphanumeric section - REVISION | - IS 1994 - N0192 - (N0303 - FCD)) | - WG 1 | - Revision | - 00/11 | - FCD - 01/11 | - 02/06 | - 02/12 |
| - JTC 1 - 18.09.04 | - ISO/IEC 9995-4: 1994 - Information technology - - Keyboard layouts for text - and office systems - Part 4 : - Numeric section - REVISION | - IS 1994 - N0193 - (N0304 - FCD) | - WG 1 | - Revision | - 00/11 | - FCD - 01/11 | - 02/06 | - 02/12 |
| - 18.09.07 | - ISO/IEC 9995-7: 1994 - Information technology - - Keyboard layouts for text - and office systems - Part 7 : - Symbols used to represent - functions - REVISION | - IS 1994 - N0194 - (N0307 - FCD) | - WG 1 | - Revision | - 00/11 | - FCD - 01/11 | - 02/06 | - 02/12 |
| - JTC 1 - 18.69 | - ISO/IEC TR 15440 - Technical Report on future - keyboards & other - associated input devices & - related entry methods | - N0120 | - WG 1 | - 96/10 | - 99/11 | - PDTR - 01/11 | - DTR - 02/11 | - TR - 03/11 |

| - Project - Number: | - Title | - Ref. | - Project - Editor | ## NP | - WD | - CD/ ### FCD | ### FDIS | ## IS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - JTC 1 - 18021 | - ISO/IEC 18021 - User interface for Mobile - tools | - N0210 - (N0306 - FDIS) | - WG 4 | - 99/06 | - 99/06 | - FCD - 01/04 | - 01/11 | - 02/04 |
| - JTC 1 - 18035 | - ISO/IEC 18035 - Icon symbols & functions for - controlling multimedia - applications | - N0190 - N0311 - CD) | - WG 2 | - 00/04 | - 01/04 | - 01/11 | - 02/06 | - 03/04 |
| - JTC 1 - 18036 | - ISO/IEC 18036 - Icon symbols & functions for - World Wide Web browsers | - N0128 - N0312 - CD) | - WG 2 | - 00/04 | - 01/04 | - 01/11 | - 02/06 | - 03/04 |
| - NWI (TR) | - Survey of existing icons and - symbols for elderly and disabled - persons | - N0316 | - WG 6 | - 01/11 |  |  |  |  |
| - NWI (TR) | - Requirements concerning icons - and symbols in IT for elderly - and disabled persons | - N0317 | - WG 6 | - 01/11 |  |  |  |  |
| - NWI (TR) - Under preparation | - Assessment of cultural and - linguistic adaptability in software - products | - WG 5 |  |  |  |  |  |  |
| - NWI (TR) - Under preparation | - Guidelines for drafting ISOIEC standards respecting cultural and linguistic adaptability principles | - WG 5 |  |  |  |  |  |  |
| - NWI (TR) - Under preparation | - Framework for user interface - standards | - WG 5 |  |  |  |  |  |  |

- 1.3 CO-OPERATION & COMPETITION

- The following people have been selected as Liaison representatives at the Sub Committee level:

- ISO/IEC SC2				Mr. Alain LaBonté

- ISO/IEC JTC 1/SC 22/WG 20		Mr. Alain LaBonté

- ISO/IEC JTC 1/SC 32			Mr. Jake Knoppers

- ISO/IEC SC 36				Dr. Yves Neuville

- ISO/TC 159/SC4			Mr. Richard Hodgkinson (acting representative)

- ISO/TC 211				Mr. Yves Hudon

- ISO/TC 145				Ms Annette Schwuchow

- IEC TC/SC 3C				Ms. Anette Schwuchow

- JWG 11 ISO/TC 145 – IEC/SC 3C	Pr. Hiroaki Ikeda

- CEN/TC 304				Mrs. Monica Ståhl

- ISO/IEC JTC 1/SC 17			Informal liaison

- GUIDE SHARE Europe			C Category liaison, Mr. Alain LaBonté

- ETSI TC HFI				C Category liaison

- ITU-T SGI				Informal Liaison

1.3.1 CO-LOCATED MEETING

The co-operation between ISO/IEC JTC 1/SC 35 and ISO/TC159/SC4 is most important and productive. A co-located meeting has already been organized in Québec from 18th to 21st November 2000 during which SC35/WG 2 and ISO/TC159/SC4/WG 5 held a one day joint meeting. They progressed there work on ISO/IEC 18035 project, “Icon Symbols and functions for controlling multimedia software applications”. The collaboration for this project is still very active. This is a good example illustrating how profitable complementary expertise and skills can be.

- 1.3.2 CLAUI TD

- SC 35 has the priority in its scope of meeting JTC 1 requirements regarding the strategic option for Cultural and Linguistic Adaptability and User Interface, (CLAUI). Forming with SC 2, SC 22/WG 20 the CLAUI Technical Direction, SC 35 makes effort to maintain close relationship with the two Sub Committees and to develop concerted work. It is expected that the CLAUI TD Coordination meeting will be held in the months to come.

- 2. PERIOD REVIEW

Two new Working groups have been created during this period:

- WG 5, Cultural, Linguistic and User Requirements (CLAUI)

- WG 6, User interfaces for disabled and elderly people

To fulfill its mission in the area of Cultural, linguistic and User Requirements, assigned by JTC 1, WG 5 is engaged in significant related work. It is preparing three New Work Items for Technical Reports to give guidance for drafting international standards respecting the CLAUI principles with a view to satisfy the users’ requirements and growing market needs in this field.

- WG 6 has prepared two New Work items for two TRs on:

- Survey of existing icons and symbols for elderly and disabled persons

- Requirements concerning icons and symbols in IT for elderly and disabled persons.

These projects are currently undergoing NP ballots.

WG 2 met two days in conjunction with ISO TC159/SC4/WG5 in November 2000 to discuss some aspects of common interest to develop the new project ISO/IEC 18035, Information technology - Icon symbols and functions for controlling multi media applications. that had been approved a few months before.

- 2.1 MARKET REQUIREMENTS

- Market requirements for SC 35 standards are driven by the rapid pace of innovation and the explosive growth of Internet applications.

- This is reflected in:

- ISO/IEC 18021, Information technology - User interfaces for mobile tools, currently under FDIS Ballot

- ISO/IEC 18035, Icon symbols and functions for controlling multimedia applications, and

- ISO/IEC 18036, Icon symbols and functions for World Wide Web browser. Both projects are currently undergoing CD ballots.

- SC 35 has considered that the rise in the elderly population of industrialized countries and the growing concern for disabled drive a stream of market requirements that can partially be addressed by SC 35 standards in the context of its scope.

- SC 35 is providing an input on icons and symbols for use by people having a weak eyesight. This is illustrated by the two new potential projects such as mentioned in paragraph 3 of Item 2 above, that are currently undergoing NP ballots.

- 2.2 ACHIEVEMENTS

- During the October 2000 through September 2001 period, SC 35 has focussed on progressing the development of projects underway and preparing five new work items.

It also produced an article published in the issue of November 2000 of the ISO Bulletin giving an overview of main SC 35 activities especially regarding icons, mobile tools and Cultural, Linguistic, and user requirements standardization.

- 2.3 RESOURCES

- Projects are well staffed and resources are adequate for the current tasks.

- SC 35 has participants with substantial expertise. However it is necessary to attract and retain new highly trained experts to deal with the CLAUI issues for example.

- 2.4 PERFORMANCE METRICS

| METRIC | 1998 | 1999* | 2000* | July 2001 |
| --- | --- | --- | --- | --- |
| Attendance to Plenaries | 12 people | 16 people | 19 people | 19 people |
| Attendance at Working groups : WG 1 | 7 | 8 | 8 | 8 |
| WG 2 | 6 | 8 | 10 | 5 |
| WG 3 | did not meet* | did not meet* | 5 | 6 |
| WG 4 | 4 | 3 | 5 | 9 |
| WG 5 |  |  |  | 8 |
| New standards published | 0 | 4 | 4 |  |
| Total Standards Published | 0 | 6 | 6 |  |
| Active projects | 14 | 8 | 9 | 11 |
| New projects | 0 | 1 | 2 | 5 |

* The figures show the attendance for the two Plenary meetings held in 1999 and in 2000.

- 3 FOCUS FOR THIS PLANNING PERIOD

- 3.1 DELIVERABLES

See section 1.2 above for projects with upcoming target dates.

3.2 STRATEGIES

SC 35 is focused on progressing its projects as timely and efficiently as possible. It feels most important to keep its focus on the need to have clear and well-defined specifications for new projects with concrete objectives that are market driven.

To achieve its mission, SC 35 is actively making efforts :

- to manage its activities effectively with the help of its ad-hoc Group on SC 35 WG Management

- to increase the number of experts within the committee and establish relationship with users, software designers, vendors and consortiums

- to be more flexible to possibly attract new comers

- to maximize its contribution to JTC 1 by seeking out New Work Items related to innovative products adding substantial value, and for which there is a market. For that purpose, it is helped by its ad-hoc Group on Emerging user interface technology

- to offer SC 35 expertise for cross-fertilization with other SC s and TCs.

3.2.1 RISKS

A risk may come from the potential proliferation of conflicting de facto standards. A second one may be raised by the decline in supporting standardization efforts for lack of time from experts.

3.2.2 OPPORTUNITIES

There are several areas of opportunity for SC 35 to cope with market requirements. Among those are :

- the CLAUI principles to be included in standards so that manufacturers be able to design products that are adapted to different languages and cultures

- the increasing Internet applications

- the growing concern for making ICT products accessible to the elderly and disabled people.

3.3 WORK PROGRAM PRIORITIES

SC 35 gives high priority to develop standardized guidelines for drafting international standards taking fully into account the CLAUI principles.